## Trang_tính1
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | sign in | Authentication | User, Shop , Shipper | User enter user name and password or login with google account to login application. | Phan Hoàng Phương | Done | iter1 | none
2 | register | Authentication | User, Shop , Shipper | User enter required options to register local account. | Phan Hoàng Phương | Done | iter1 | none
3 | reset password | Authentication | User, Shop , Shipper | User enter email and system will send link redirect to change password page. User enter new password and password will be updated. | Phan Hoàng Phương | Done | iter1 | none
4 | Verify Email | Authentication | User, Shop , Shipper | User enter email and enter OTP that have been sent to that email | Phan Hoàng Phương | Done | iter1 | none
5 | User home page | Ordering | User | User can view home page with offering foods | Phan Hoàng Phương | Done | iter1 | none
6 | Shop home page | Manage Profile | Shop | Shop can view Coming order | Phan Hoàng Phương | Done | iter1 | none
7 | Shipper Home Page | Ordering | Shipper | Shipper can view their current order that need delivery | Phan Hoàng Phương | Done | iter1 | iter2
8 | Dashboard | Platform Management | Admin | Admin can view platform statistic | Phan Hoàng Phương | Done | iter1 | iter2
9 | Food Information | Ordering, Manage Profile | User, Shop | Display Food information and Shop can adjust it | Phan Hoàng Phương | Done | iter1 | iter2
10 | Shop Information | Ordering, Manage Profile | User, Shop | Display Shop information and Shop can adjust it | Phan Hoàng Phương | Done | iter1 | iter2
11 | Ticket | Support | User | Allow user to write ticket to admin to demand support | Phan Hoàng Phương | Done | iter1 | iter2
12 | Top up | Payment | User | Fill in amount of money to top up to wallet | Phan Hoàng Phương | Done | iter1 | iter2
13 | Payment | Payment | User | Pay for the top up | Phan Hoàng Phương | Done | iter1 | iter2
14 | Cart | Ordering | User | View and manage items in cart | Phan Hoàng Phương | Done | iter1 | iter2
15 | Map | Ordering | User, Shop | Pick Location | Phan Hoàng Phương | Done | iter1 | iter2
16 | Search Result | Ordering | User | Search for food and shop | Phan Hoàng Phương | Done | iter1 | iter2
17 | Orders | Ordering | User, Shop , Shipper | Displays all current orders that involved user | Phan Hoàng Phương | Done | iter1 | iter2
18 | Orders detail | Ordering | User, Shop , Shipper | Display detailed information of order | Phan Hoàng Phương | Done | iter1 | iter2
19 | Profile | Manage Profile | User, Shop , Shipper | Allow User to view their own profile | Phan Hoàng Phương | Done | iter1 | iter2
20 | Update Profile | Manage Profile | User, Shop , Shipper | Allow User to manage their own profile | Phan Hoàng Phương | Done | iter1 | iter2
21 | Update password | Manage Profile | User, Shop , Shipper | Allow user to update new password for their account | Phan Hoàng Phương | Done | iter1 | iter2
22 | Update Contact | Manage Profile | Shop | Allow shop to update new contact information of their own shop | Phan Hoàng Phương | Done | iter2 | none
23 | Wallet | Manage Profile | Shop, Shipper | allow user to view their wallet | Phan Hoàng Phương | Done | iter2 | none
24 | User Management | Platform Management | Admin | Allow admin to manage users on platform | Phan Hoàng Phương | Done | iter2 | none
25 | Shop Management | Platform Management | Admin | Allow admin to manage shops on platform | Phan Hoàng Phương | Done | iter2 | none
26 | Shipper Management | Platform Management | Admin | Allow admin to manage shippers on platform | Phan Hoàng Phương | Done | iter2 | none
27 | Shop Approving | Platform Management | Admin | Allow Admin to approve newly registerd shop account | Phan Hoàng Phương | Done | iter2 | none
28 | Shipper Approving | Platform Management | Admin | Allow Admin to approve newly registerd shipper account | Phan Hoàng Phương | Done | iter2 | none